## README
READ ONLY - please duplicate before using
This is a READ ONLY version of the tool - please continue to read on how to copy this so you can use it
Please read this important setup information
Welcome to the eNASSS-CAT toolkit. Please take the time to read these guidelines and instructions as they will help you get the most out of the tools. There are 5 key steps to getting started.
Which version are you using?
There are two versions of the tools available - a Google Sheets version and a Microsoft Office 365 version. Both offer the same functionality and there’s no “right” or “wrong” version to use. There are some subtle differences between Google Sheets and Microsoft Office 365, namely around navigating through the tools and collaborating with other users. We go into further detail about the differences below in our 5 step guide.
5 steps to getting started
1. Supported devices
The tools have been designed to work principally on desktop and laptop devices and be platform agnostic - so they should work the same on Windows, Mac and Linux. These tools will more than likely work on smartphones too however they have not been optimized for usage on these small devices, so you may have to “zoom” in and out to view the contents and interact with them. We would recommend using a desktop/laptop computer to make the most out of the tools.
2. Duplicate file/save locally
After you registered your interest in using the tool on the dedicated website, you will have accessed the link to either the Google Sheets or Microsoft Office 365 (excel) version. You are more than likely reading this page using that same link that was provided to you.
| ! | It’s essential that you duplicate this tool and store it locally within your own person/work/corporate account.
If you are using Google Sheets:
| ‣ | Sign-in to your Google account. Use the Google account that you want this tool to be stored under.
| ‣ | Load up this tool - if you’ve signed in after loading up the tool, you may need to refresh this page
| ‣ | Click File and select Make a copy
| ‣ | Enter a name for the file and under Folder select a location where you want the tool to be stored. If you have a Google Apps account or use Share Folders, you may want to select a folder that multiple people in your organisation can access.
| ‣ | Ensure that the Share it with the same people option is not selected
| ‣ | Click OK - a new tab/window should open with the duplicated tool
If you are using Microsoft Office 365:
| ‣ | Download a copy of the excel sheet from the link provided.
| ‣ | Select the Folder where you want the tool to be stored and click Save.
| ‣ | If you use Sharepoint or Shared Folders, you may want to select a folder that multiple people in your organisation can access.
| ? | Once you duplicate this tool, it’s important to understand that no one else can access the tool and data stored within it unless you explicitly share it with people or place it on a shared drive/folder that other people have access to. The team who developed the NASSS-CAT tools will not have access to any data that you input into it.
3. Navigation in the tools
The tools are split into multiple sections (or tabs) to make it easier to interact with them and enter data section by section. There are two ways of navigating through the tools:
| ‣ | Using the tabs at the bottom of the screen Depending on which tool you are using, the number of tabs may vary but there will always be tabs for README and Introduction. You can click on each of the tabs to navigate through the sections.
| ‣ | Using the navigation buttons at the top and bottom of each section At the top and bottom of each section, you should see a consistent header/bar with the eNASSS-CAT logo and either one or two blue buttons (Previous section / Next section). You can use these buttons to move between tabs/sections.
Please note: When using Google Sheets, clicking on the buttons will open a drop-down menu and you then have to further click on the page listed to navigate between sections
4. Inviting users to collaborate on tools and project
A key part of using the eNASSS-CAT tools is collaborating with colleagues. Rather than sending a copy of the tool to colleagues on email (which causes problems when multiple people want to contribute at the same time), you can use the power of online collaboration to invite people to the tool and contribute in real-time. There are different ways of achieving this, depending on which version of the tool you are using:
If you are using Google Sheets:
| ‣ | Select the green Share button in the top right of the window
| ‣ | Under Add people and groups enter the email address of the person you wish to invite to contribute
| ‣ | You can specify multiple email addresses/people - just hit the return key after each email and you should be able to enter another
| ‣ | You may enter an optional message in the Message box. This is usually a good idea so the recipient knows why they are being invited to contribute. If you can’t see the Message box make sure the Notify people option is checked.
| ‣ | Click the Send button - You may be prompted to confirm that you are happy to share this file outside of your organisation. Click Share anyway
| ‣ | Colleagues do not need to have a Google account in order to contribute
If you are using Microsoft Office 365:
| ‣ | Select the green Share button in the top right of the window
| ‣ | Under To: Name, group or email enter the email address of the person you wish to invite to contribute
| ‣ | You can specify multiple email addresses/people - just hit the return key after each email and you should be able to enter another.
| ‣ | You may enter an optional message in the Message... box. This is usually a good idea so the recipient knows why they are being invited to contribute.
| ‣ | Click the Send button
| ‣ | Colleagues do not need to have a Microsoft account in order to contribute
5. Exporting/saving outputs
You may wish to export some or all of the contents of the tool to share with your colleges or to save a copy for future reference. There are a number of ways this can be achieved:
Copying figures & charts
Any charts (such as pie and radar charts) and images within the tool can be copied by single-clicking on them and then selecting Edit and Copy. These can then be pasted into most software like PowerPoint, Word, emails etc.
Print / Export PDF
You may want to export a section/tab too - such as the results or overview sections. You can do this by selecting File and then Print. You may want to adjust the settings such as Orientation and Scaling so that the entire contents of the tab is readable or it fits onto a single sheet of paper. If you have an Adobe PDF reader (or equivalent) installed on your computer, you should have the option to select PDF from the drop-down of printers installed on your computer. This will then allow you to save the file as a PDF rather than physically printing it.
i | You can delete this README tab Once you’ve read through this information and understood how to use the tool, you may wish to delete this tab from the tool so that other users don’t see it. You can do this by right-clicking on the tab name and selecting “Delete”.

## Introduction
Your work will save automatically if you are using Office 365 or Google Docs
Next section
eNASSS-CAT Project
For monitoring project complexity over time
© IRIHS group and mHabitat
Introduction
The Project version of the eNASSS-CAT is intended to be used when you are setting up and running a specific project to implement a new technology in a health or care setting. You may be asked to complete it more than once as the project unfolds. Go to the Questions tab to complete the assessment.
|  | ! | Note: this tool will only give you a semi-quantitative estimate because some aspects of a project will be more important than others
|  | i | To make the most of this toolkit, please visit the online help sections for how to use:
|  |  | • Google Sheets | Next section
• Office365

## Questions
Your work will save automatically if you are using Office 365 or Google Docs
|  |  |  | Previous section | Next section
Instructions
This tool looks at five groups of complexities that may apply to your project: strategic, technical, operational, people-related and 'political' complexity. For each of the statements in each group, select whether you 'agree' or 'disagree'. Some statements may not apply to your project, so select ‘not applicable’ for these. If a statement seems relevant but you’re not sure how to answer it, select ‘don’t know’ – and perhaps discuss this one with colleagues later. Then think about whether this area is likely to get more complex in the next phase of your project. If so, select 'yes' in the blue column. This will help to plot emergent complexity.
|  | STRATEGIC COMPLEXITIES |  | Response at current time? | Likely to get more complex in next phase?
The vision and benefits for the project are not yet clear
The fit between this technology and the organisation’s mission and strategy is poor
The business case for the work is unclear or contested
The scope of the project is unclear or contested
The work will have major knock-ons for other key projects and business-as-usual operations
Success criteria are not yet explicitly set out and agreed by key stakeholders
The project’s success could be threatened by external changes that impact on the organisation
|  | TECHNICAL COMPLEXITIES |  | Response at current time? | Likely to get more complex in next phase?
The technology does not yet exist in a robust and dependable form
The technology is unfamiliar to the project team
The technology supply chain is not yet in place
The technology cannot be installed until the system is upgraded (e.g. hardware, bandwidth)
A key technology needs to be installed across multiple technical systems to achieve ‘integration’
Introducing the technology will require significant changes in care pathways and organisational routines
Quality standards and regulatory requirements for using the technology in a health/care setting have not been fully defined (or key stakeholders don’t know about them or accept them)
|  | OPERATIONAL COMPLEXITIES |  | Response at current time? | Likely to get more complex in next phase?
A schedule and resource plan have not yet been defined
The pace of the project (time to achieve key goals and milestones) seems unachievable
The budget is insufficient for the task or there is limited flexibility in how the budget can be used
Resources (e.g. test facilities, equipment) may not be available when needed
Evaluation measures and metrics have not yet been agreed
Accurate, timely and comprehensive data reporting will be difficult or impossible
New management tools and data sources will be needed to guide, monitor and evaluate the project
|  | PEOPLE-RELATED COMPLEXITIES |  | Response at current time? | Likely to get more complex in next phase?
The people leading the project are inexperienced in this kind of work
The people leading the project do not have adequate control over project staff (e.g. no direct reporting)
There are not yet sufficient people with the right skills available to participate in the project.
There are no key people who are wholly allocated to the work for the project
Lines of responsibility for tasks and deliverables are not yet defined
Team members have limited confidence in the technology or do not fully understand how to use it
Team members have limited motivation and are not yet functioning well as a team
|  | "POLITICAL" COMPLEXITIES |  | Response at current time? | Likely to get more complex in next phase?
The work does not have a senior sponsor in the organisation who recognises its importance and helps negotiate its progress
The senior management team in the relevant department does not fully support the work
Substantial work will be needed to bring people on board and develop a shared vision for the change
People beyond the core team don’t understand the project or have unrealistic expectations for it
People beyond the project team don’t support the project or are not aligned or have insufficient time
The core team does not have the authority to make decisions
The work will require cooperation across sectors (e.g. health / social care)
|  |  | Previous section |  | Next section

## Ref (hidden)
Section | Agree score | Complex score
STRATEGIC | 0 | 0
TECHNICAL | 0 | 0
OPERATIONAL | 0 | 0
PEOPLE-RELATED | 0 | 0
"POLITICAL" | 0 | 0
| Agree | Disagree | Likely to get more complex in next phase | Not applicable | Don't know
STRATEGIC | 0 | 0 | 0 | 0 | 0
TECHNICAL | 0 | 0 | 0 | 0 | 0
OPERATIONAL | 0 | 0 | 0 | 0 | 0
PEOPLE-RELATED | 0 | 0 | 0 | 0 | 0
"POLITICAL" | 0 | 0 | 0 | 0 | 0
Agree

## Results
Your work will save automatically if you are using Office 365 or Google Docs
Previous section
RESULTS
The charts below provide visualisations of the different complexities assessed by you on the previous page. • The first two radar charts show your assessment of current (left) and emergent (right) complexity across all of the complexity groups. The further out the lines on the radar charts go, the more complex that particular domain is. The closer the lines are to the centre, the less complex that particular domain is. • The pie charts underneath show your assessments made within each of the complexity groups.
| ! | Should you wish to use the charts below in other documents or presentations, you can select a chart below and copy (CTRL + C on Windows or CMD + C on Mac) and paste them into other software.